## second qtr 2022
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE MONTH ENDED JUNE 30, 2022
Program of Project / Source | Location | Total Cost | Date Started | Target Completion Date | Projecct Status |  |  | No. of Extensions if any | Remarks
[5 empty] | % of completion | Total Cost Incurred to Date | Balance
Sen. Manuel Villar | various - For Medical Missions purchase of medecines (CHO - Bac City) | 1500000 | 2012-02-21 | 2012-03-26 | 100% | 1497420.8 | 2579.2 |  | Already return to Natl. Bureau of Treas
EMERCIANO DE JESUS | Tuition fees and miscellaneous - various (Bac City) | 150000 | 2011-11-08 | 2013-06-27 | 65% | 97840 | 52160 |  | Already return to Natl. Bureau of Treas
AKBAYAN | Pur of med Indigents patients - Doña Corazon Mon. Mem. Hospital,Bacolod City | 150000 | 2011-02-11 | 2011-02-17 | 100% | 150000 | 0 |  | Completed
Homer Mercado | various - Livelihood program | 100000 | 2011-09-06 | 2015-12-31 | - | 0 | 100000 |  | Already return to Natl. Bureau of Treas
Sen. Franklin Drilon | Rehabilitation of Pub. Plaza - Bacolod City | 1000000 | 2011-03-18 | 2012-04-24 | 100% | 993810.85 | 6189.15 |  | Already return to Natl. Bureau of Treas
Sen. Juan Ponce Enrile | Installation of Streetlights along Circumferential road - Bacolod City | 5000000 | 2012-01-27 | 2018-06-27 | 93% | 4676014.6 | 323985.4 |  | Already return to Natl. Bureau of Treas
Francis Escudero | Repair of Public market roofing/gutters - Bacolod City | 500000 | 2011-09-21 | 2012-10-17 | 96% | 480095.8 | 19904.2 |  | Already return to Natl. Bureau of Treas
Neri Colmenares | Negros Press Club (OFW) | 200000 | 2011-05-24 | 2012-11-20 | 100% | 200000 | 0 |  | Completed
Bayan Muna Partylist | Fin. Assis for the Bac City Public Plaza Services office/PESO / OFW | 200000 | 2013-01-31 | 2013-07-24 | 72% | 145149.96 | 54850.04 |  | Already return to Natl. Bureau of Treas
Neri Colmenares | F/A for the Radio Program Legal assistance -IBP | 100000 | 2013-01-31 | 2021-12-31 | - | 0 | 100000 |  | Already return to Natl. Bureau of Treas
Sen. Teofisto Guingona | Fin assistance to Indigents patients, Doña Corazon Mon. Mem. Hospital,Bac City | 500000 | 2011-03-18 | 2012-12-03 | 100% | 500000 | - |  | Completed
Sen. Teofisto Guingona | Assistance to Indigent & Displaced Families - Bac City | 1500000 | 2012-01-27 | 2013-05-07 | 99% | 1487265 | 12735 |  | Already return to Natl. Bureau of Treas
Sen. Teofisto Guingona | Road Concreting Purok Kabulakan - Brgy Singcang Airport | 1000000 | 2012-01-27 | 2012-12-31 | 100% | 997169.12 | 2830.88 |  | Already return to Natl. Bureau of Treas
Sen. Teofisto Guingona | Road Concreting of UNO-R Ville Subd. - Brgy Mansilingan | 500000 | 2012-01-27 | 2012-10-09 | 100% | 499207.77 | 792.23 |  | Already return to Natl. Bureau of Treas
Teodoro Haresco JR | Fin assitance - BAITODA, Inc. | 200000 | 2012-07-03 | 2012-08-15 | 100% | 200000 | 0 |  | Completed
Juan Miguel Zubiri | Fin assistance - St. John Institute | 1000000 | 2010-02-02 | 2010-02-04 | 100% | 1000000 | 0 |  | Completed
Juan Miguel Zubiri | Fin assistance - St. John Institute | 500000 | 2009-10-23 | 2010-01-08 | 100% | 500000 | 0 |  | Completed
Sen. Mar Roxas | Repair & Renovation of Bacolod Central Market - Bac City | 1016906.89 | 2009-03-23 | 2010-12-13 | 100% | 1014955.95 | 1950.94 |  | Already return to Natl. Bureau of Treas
Teodoro Casino | Sports program - Bacolod City | 200000 | 2014-03-27 | 2014-12-11 | 100% | 200000 | - |  | Completed
Sen Teofisto Guingona | Food Subsidy Scholarship and Medical assistance - Brgy Singcang Airport | 80000 | 2014-03-27 | 2015-03-30 |  | 0 | 80000 |  | Already return to Natl. Bureau of Treas
Cong. Emmeline Aglipay | Fin. Assistance for trycle drivers in Granada | 100000 | 2014-03-27 | 2015-03-30 |  | 0 | 100000 |  | Already return to Natl. Bureau of Treas
Cong. Emmeline Aglipay | Priority Devt. Program | 500000 | 2010-12-14 | 2015-03-30 |  | 0 | 500000 |  | Already return to Natl. Bureau of Treas
Emmeline Aglipay | Kilos Asenso Program | 954322 | 2010-05-06 | 2015-05-30 |  | 0 | 954322 |  | Already return to Natl. Bureau of Treas
Senator Ramon Magsaysay | DSWD - Gawad Kalinga Core Shelter | 2000000 | 2009-06-15 | 2015-05-30 |  | 0 | 2000000 |  | Already return to Natl. Bureau of Treas
Ramon Magsaysay | Improvement of BCPO facilities - BCPO | 27033 | 2007-01-01 | 2015-05-30 |  | 0 | 27033 |  | Already return to Natl. Bureau of Treas
Ramon Magsaysay | Set up for Beginning balance | 0.7 | 2007-01-01 | 2015-05-30 |  | 0 | 0.7 |  | Already return to Natl. Bureau of Treas
Ramon Magsaysay | Rural Health units | 2500 | 2007-01-01 | 2015-05-30 |  | 0 | 2500 |  | Already return to Natl. Bureau of Treas
Ramon Magsaysay | Impt. of Plaza, Parks & Othe Public Infra. | 1015246 | 2007-01-01 | 2009-09-10 | 100% | 1015194 | 52 |  | Already return to Natl. Bureau of Treas
Cong. Cinchona Cruz-Gonzalez | Replacement of Artesian wells in various barangays - Bacolod City | 350000 | 2009-02-06 | 2011-08-15 | 100% | 348078.77 | 1921.23 |  | Already return to Natl. Bureau of Treas
Cong. Cinchona Gonzales | BUREAU OF TREASURY - set up for beginning balance (NALGU) | 100000 | 2007-01-01 | 2015-05-30 |  | 0 | 100000 |  | Already return to Natl. Bureau of Treas
Cong. Cinchona Gonzales | Priority Dev. Program & Projects | 9934.01 | 2007-01-01 | 2015-05-30 |  |  | 9934.01 |  | Already return to Natl. Bureau of Treas
Cong. Cinchona Gonzales | Set up for Beginning balance | 4000 | 2007-01-01 | 2015-05-30 |  |  | 4000 |  | Already return to Natl. Bureau of Treas
Cong. Cinchona Cruz-Gonzalez | Maint. Plaza parks, City hall & Other public infra | 1000000 | 2008-05-29 | 2011-10-31 | 100% | 996548 | 3452 |  | Already return to Natl. Bureau of Treas
Cong. Cinchona Cruz-Gonzalez | Rehabilitation of drainage line - Aguinaldo Brgy. 4, Bac City | 10000000 | 2011-03-18 | 2013-06-10 | 100% | 9984774.37 | 15225.63 |  | Already return to Natl. Bureau of Treas
T O T A L |  | 31459942.6 |  |  |  | 26983524.99 | 4476417.61
| (SGD) |  | (SGD)
| ATTY. JEREMAE ANN T. CERIACO, CPA |  | HON. ALFREDO ABELARDO B. BENITEZ
| ACTING CITY ACCOUNTANT |  | CITY MAYOR